## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
Sprint 01 Plan
| Sprint 01 Plan | Sprint 01 Plan - Sprint 01 Plan
Sprint 01 Plan - Sprint 01 Plan
| Table 1 | Sprint 01 Plan - Sprint 01 Plan
Sprint 1 Burndown Chart
| Sprint 1 | Sprint 1 Burndown Chart - Sprin
Sprint 01 Execution - Sprint 01
| Table 1 | Sprint 01 Execution - Sprint 01
Sprint 02 Plan
| Table 1 | Sprint 02 Plan
Sprint 02 Execution - Sprint 02
| Table 1 | Sprint 02 Execution - Sprint 02
Sprint 2 Burndown Chart
| Sprint 2 | Sprint 2 Burndown Chart - Sprin

## Sprint 01 Plan - Sprint 01 Plan
Sprint 01 Plan
User Stories | Tasks | Dependency | Story Points | Tuesday | Wednesday | Thursday | Friday | Saturday
1 | 1 |  | 1 | MV:1
1 | 2 |  | 1 |  | A:1
1 | 3 | T2 | 1 |  | A:1
1 | 4 | T1 | 2 |  | B:2
1 | 5 | T4 | 5 |  |  | A:5
1 | 6 | T1 | 5 |  |  | MZ:2 | MZ:3
1 | 7 | T5, T6 | 3 |  |  |  |  | MZ:3
2 | 8 |  | 5 |  | V:3 | V:2
2 | 9 | T5 | 8 |  |  |  | B:5 | B:3
2 | 10 | T2 | 3 |  |  | MV:3
2 | 11 | T4 | 5 |  |  |  | MV:5
2 | 12 | T4 | 5
2 | 13 | T8,T11, T12 | 2

## Sprint 1 Burndown Chart - Sprin
Sprint 1
| Actual | Provisional
Start | 39 | 39
Tuesday | 38 | 38
Wednesday | 36 | 34
Thursday | 36 | 21
Friday | 26 | 11
Saturday | 21 | 0
Sunday | 13 | 0

## Sprint 01 Execution - Sprint 01
Sprint 01 Execution
User Stories | Tasks | Dependency | Story Points | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
1 | 1 |  | 1 | MV:1
1 | 2 |  | 1 |  | A:1
1 | 3 | T2 | 1 |  | A:1
1 | 4 | T1 | 2 |  | B:3 |  |  | B:1
1 | 5 | T4 | 5 |  |  | A:5 | A:1
1 | 6 | T1 | 5 |  |  | MZ:2 | MZ:3
1 | 7 | T5, T6 | 3 |  |  |  |  | MZ:3
2 | 8 |  | 5 |  | V:3 | V:2
2 | 9 | T5 | 8 |  |  |  | B:2 | B:2 | B:1
2 | 10 | T2 | 3 |  |  |  | MV:2 | MV:1

## Sprint 02 Plan
Sprint 02 Planning
User Stories | Tasks | Dependency | Story Points | Tuesday | Wednesday | Thursday | Friday | Saturday
2 | 8 |  | 1 |  |  | V:1
2 | 11 |  | 5 |  | MV:3 | MV:2
2 | 12 |  | 3 |  |  | A:3
2 | 13 | T8,T11, T12 | 2 |  |  |  | V:2
2 | 14 |  | 3 |  |  |  |  | B:3
3 | 15 | T13 | 5 |  |  |  |  | MV:5
3 | 16 | T14 | 8 |  |  |  |  | MZ:3
3 | 17 | T15, T16 | 2

## Sprint 02 Execution - Sprint 02
Sprint 02 Execution
User Stories | Tasks | Dependency | Story Points | Tuesday | Wednesday | Thursday | Friday | Saturday
2 | 8 |  | 1 |  |  | V:1
2 | 11 | T4 | 5 |  |  |  | MV: 5
2 | 12 | T4 | 3 |  |  | A:3
2 | 13 | T8,T11, T12 | 2
2 | 14 |  | 3 |  |  |  |  | B:3
3 | 15 | T13 | 5
3 | 16 | T14 | 8 |  |  |  |  | MZ:1

## Sprint 2 Burndown Chart - Sprin
Sprint 2
| Actual | Provisional
Start | 22 | 22
Wednesday | 22 | 22
Thursday | 18 | 13
Friday | 13 | 11
Saturday | 10 | 3